## IBA
S.No | Jira ID | Jira Name | Assigned To | Logged Hours in Jira for dev | Logged hours in jira for tester | Dev in hr | Testing in hr | Dev Status | Comments
1 | IBA-806 | Create functionality to redirect to Verification screen | Praveen | 12h | 30 minutes | 12 | 4 | Completed | Waiting for Workflow check once received end point from haritha
2 | IBA-807 | Add "Resend verification code by text?" link to verification screens in signup and forget password | Praveen | 8h | 2.5 h | 4 | 1 | Completed | Waiting for Workflow check once received end point from haritha
3 | IBA-808 | Send the same verification code on resend code click | Haritha | 1h | 15 minutes | 1 | 0.5 | Completed | Waiting to push the code
4 | IBA-809 | Include Send by sms functionality- backend | Haritha | 12h 10min | 1h | 15 | 3 |  | End date for dev:14-July-2020
5 | IBA-810 | Preparation of Regression test case for verification code and Send by sms functionality | Sasi |  | 1.5h |  | 1.5
6 | IBA-811 | Regression testing for new enhancement Email and text message | Sasi |  | 1.5 h | 32 | 10
Total |  |  |  | 40 h 25 minutes