## NT
S.No | Jira ID | Jira Name | Assigned To | Estimated hrs | Follow ups | Action
1 | NT-337 | Treat Fruits & veggies separate from Carbs and calculate the calories for both of them separately | Bhuvaneshwari | 1d 2h | 2 client issues | Need to fix PDF 1 FRECH VERSION IN FRONT END DOWNLAOAD and send an email | Sent
2 | NT-338 | Add a new meal plan table in the example page instead of the current set of text below the example page image | Bhuvaneshwari | 1d 2h | Ingredient | Bhuvana need to update | Updated
3 | NT-339 | Add the new table for mapping grams with slices and also make it editable from the frontend just like the food options | Bhuvaneshwari | 3d 6h | Feedback DOCUMENT for PDF2 | Done
4 | NT-342 | Update the image in the example page for both English and French versions | Bhuvaneshwari | 2h | Example page indd need | need to fix the bug from bhuvana
Total |  |  |  | 52h | Remove legends | done
[5 empty] | Harithas front end changes | Waiting for testing
[5 empty] | Alignment issue in PDF | Waiting for testing
|  | http://jira.asahitechnologies.com:8080/browse/NT-343 |  |  | Recommend you add in Both language | Waiting for testing
http://jira.asahitechnologies.com:8080/browse/NT-344
http://jira.asahitechnologies.com:8080/browse/NT-345
http://jira.asahitechnologies.com:8080/browse/NT-346
http://jira.asahitechnologies.com:8080/browse/NT-347

## IBA
S.No | Jira ID | Jira Name | Assigned To | Logged Hours in Jira for dev | Logged hours in jira for tester | Dev in hr | Testing in hr | Dev Status | Comments
1 | IBA-806 | Create functionality to redirect to Verification screen | Praveen | 12h | 30 minutes | 12 | 4 | Completed | Waiting for Workflow check once received end point from haritha
2 | IBA-807 | Add "Resend verification code by text?" link to verification screens in signup and forget password | Praveen | 10h 20 mins | 3.5 h | 4 | 1 | Completed | Waiting for Workflow check once received end point from haritha
3 | IBA-808 | Send the same verification code on resend code click | Haritha | 1h | 15 minutes | 1 | 0.5 | Completed | Waiting to push the code
4 | IBA-809 | Include Send by sms functionality- backend | Haritha | 12h 10min | 1h | 15 | 3 |  | End date for dev:14-July-2020
5 | IBA-810 | Preparation of Regression test case for verification code and Send by sms functionality | Sasi |  | 1.5h |  | 1.5
6 | IBA-811 | Regression testing for new enhancement Email and text message | Sasi |  | 1.5 h | 32 | 10
Total |  |  |  | 43 h 45 minutes