## Sheet 1
Issue | Worklog Reporter | Worklog Day | Summary | Worklog Comment | Time Logged
NT-328 - Height inches to cm and cm to inches(CR from client)
| Haritha R | Jun/23/2020 | Height inches to cm and cm to inches(CR from client) | I gone through the code of nutreetion for height conversion | 1.5
| Haritha R | Jun/24/2020 | Height inches to cm and cm to inches(CR from client) | I worked to convert the Heights from inches to cm in nutreetion application with providing the validations | 1.3333
| Sasireka C | Jun/24/2020 | Height inches to cm and cm to inches(CR from client) | Tested the height conversion and pdf alignment for both languages | 0.5
3.3333
NT-329 - Intake calories tab:Change as text box for Crabs, protein ad fat fields and edit the values with proper validation
| Haritha R | Jun/24/2020 | Intake calories tab:Change as text box for Crabs, protein ad fat fields and edit the values with proper validation | Made the three fields as editable. | 1.6667
| Haritha R | Jun/24/2020 | Intake calories tab:Change as text box for Crabs, protein ad fat fields and edit the values with proper validation | Discussed with Sasi, Bhuvi and Rahul regarding the exact functionality and confirmed | 0.5
| Sasireka C | Jun/24/2020 | Intake calories tab:Change as text box for Crabs, protein ad fat fields and edit the values with proper validation | Tested the intake calories and raised one issue to haritha | 0.5
| Sasireka C | Jun/24/2020 | Intake calories tab:Change as text box for Crabs, protein ad fat fields and edit the values with proper validation | Retested the bugs and works fine in staging and sent mail to client to test and review the Nutrition project | 0.25
2.9167
NT-330 - Rename Macronutrients as "Food priority"
| Haritha R | Jun/24/2020 | Rename Macronutrients as "Food priority" | I renamed to Food Priority | 0.25
| Sasireka C | Jun/24/2020 | Rename Macronutrients as "Food priority" | Tested the Nutrition plan preference page with the text macronutrient to Food priority | 0.25
0.5
NT-331 - Nutrition Plan preference: Remove recommendation pop up and click on Generate meal plan will download the PDF
| Haritha R | Jun/24/2020 | Nutrition Plan preference: Remove recommendation pop up and click on Generate meal plan will download the PDF | Removed recommendation pop up and click on Generate meal plan will download the PDF | 2.5
| Sasireka C | Jun/24/2020 | Nutrition Plan preference: Remove recommendation pop up and click on Generate meal plan will download the PDF | Tested the recommendation pop up removed after review page in staging site | 0.5
3
NT-332 - Remove exclusion in both PDF
| Bhuvaneshwari Shanmugavadivel | Jun/24/2020 | Remove exclusion in both PDF | Removed the exclusion from eng and french pdf | 0.3333
| Sasireka C | Jun/24/2020 | Remove exclusion in both PDF | tested the pdf1 and pdf2 example page doesnot contain exclusion | 0.1667
0.5
NT-333 - In back end exclusion recommendation as 15 default
| Haritha R | Jun/24/2020 | In back end exclusion recommendation as 15 default | provided the default value for recommendation | 0.5
| Sasireka C | Jun/24/2020 | In back end exclusion recommendation as 15 default | Tested in front end pop up not displayed so the default will be 15 | 0.25
0.75
133.3333